## Sheet1
Day | Goals for the day | Duration | Complexity
2022-09-21 | Create a plan timeline | 1 day | Easy
2022-09-22 | Set up Azure Cloud Shell | Half day | Easy
2022-09-22 | Configure Github Actions | Half day | Easy
2022-09-23 | Continous Delivery on Azure | 1 day | Hard
2022-09-24 | Documentation | Half day | Hard
2022-09-25 | Demo | Half day | Medium
2022-09-26 | Result evaluation | Half day | Medium
| Goals | Goals
| Create a plan timeline | Done
| Set up Azure Cloud Shell | Done
| Configure Github Actions | Done
| Continous Delivery on Azure | Done
| Documentation | Done
| Demo | Done
| Result evaluation | Done