## day plan
Day | Goals for the day | Duration | Complexity
2022-09-21 | Create a plan timeline | 1 day | Easy
2022-09-22 | Set up Azure Cloud Shell | Half day | Easy
2022-09-22 | Configure Github Actions | Half day | Easy
2022-09-23 | Continous Delivery on Azure | 1 day | Hard
2022-09-24 | Documentation | Half day | Hard
2022-09-25 | Demo | Half day | Medium
2022-09-26 | Result evaluation | Half day | Medium
| Goals | Goals
| Create a plan timeline | Done
| Set up Azure Cloud Shell | Done
| Configure Github Actions | Done
| Continous Delivery on Azure | Done
| Documentation | Done
| Demo | Done
| Result evaluation | Done

## year and quarter goal
Week Number | Week (DD/MM/YYYY) | Quarter Goal | Year Goal
1 | 2022-10-05 | Q4: Working and Functioning CI/CD Pipeline in Azure, that deploys an Azure Flask webapp providing Boston Housing Price Prediction based on input parameters, given in a POST request. Setup Github Actions and Azure Pipelines for the Webapp.. | Working CI/CD Azure Pipeline App with well documented, platform independent code
2 | 2022-10-12
3 | 2022-11-19
4 | 2022-12-26
5 | 2023-01-03 | Q1: Add and update documentation, requirements.txt and add screenshots of working app. Add code walkthrough, outlining steps and install older versions of Python 3.7 on Azure Shell.
6 | 2023-02-10
7 | 2023-02-17
8 | 2023-03-24
9 | 2023-03-30
10 | 2023-04-03 | Q2 : Talk to stakeholders and add new features
11 | 2023-05-10
12 | 2023-05-17
13 | 2023-06-24
14 | 2023-06-30
15 | 2023-07-03 | Q3: regular maintenance activity to be planned
16 | 2023-08-10
17 | 2023-09-17
18 | 2023-09-24